## Q2 Roadmap
Milestone | Owner | Due | Status | Notes
Onboarding v2 design freeze | Koichi Ikeno | 2026-04-18 | Done | Figma v2 approved
PROD-1327 fix shipped | Mitsuhiro Suzuki | 2026-05-09 | In progress | Blocking launch
Beta cohort (50 users) | Shota Gushima | 2026-05-30 | In progress | Recruiting via #product-dev
Activation dashboard live | Rei Kawaji | 2026-06-06 | Not started | Needs analytics access
GA launch | Shota Gushima | 2026-06-27 | Not started | Gate: beta NPS ≥ 40